## Backlog
ID | Product Backlog Item | Assignee | Priority | Difficulty | EST(Hrs) | Status
14 | Implement a seed class | Jonathon | MID | HIGH | 3 | open
18 | Minimax tree used for AI | Xiaoyu | MID | HIGH | 5 | open
19 | Computer looks ahead one move in tree | Xiaoyu | MID | HIGH | 3 | open
20 | Computer can randomly select a valid move | Andrew | MID | HIGH | 4 | open
21 | Computer identifies all valid moves | Andrew | MID | HIGH | 3 | closed
23 | separate GUI into screens | Xiaoyu | HIGH | HIGH | 3 | closed
24 | merge project into MVC framework | Jonathon | HIGH | MID | 2 | closed
25 | turn clock ends turn if expired | Jonathon | MID | MID | 2 | open
26 | variable amount of houses | Xiaoyu | HIGH | MID | 3 | closed
27 | variable amount of seeds | Jonathon | HIGH | LOW | 1 | closed
28 | difficulty selector | Jonathon | HIGH | LOW | 1 | closed
29 | rules/tips documentation | Xiaoyu | LOW | LOW | 1 | closed
30 | pie rule | Andrew | HIGH | HIGH | 3 | closed
31 | random distribution of seeds | Xiaoyu | HIGH | HIGH | 3 | open
32 | integrate client/server model | Jonathon | HIGH | MID | 3 | open
33 | settings/pause menu | Xiaoyu | LOW | MID | 2 | open
34 | display seeds on board | Xiaoyu | HIGH | MID | 3 | open
35 | possible moves | Andrew | HIGH | MID | 3 | open
36 | result of possible moves | Jonathon | HIGH | MID | 3 | open
37 | board evaluation/utility function | Andrew | HIGH | MID | 2 | open
38 | best/greedy move right now | Jonathon | MID | HIGH | 3 | open

## Sprint2
Sprint Goal | Volunteer | Original Estimate | 2017-03-22 | 2017-03-24 | 2017-03-26 | 2017-03-28 | 2017-03-30 | 2017-04-01 | 2017-04-03 | 2017-04-05 | 2017-04-07 | Sprint Review
Allow an AI to play random moves against a player, add client/server functionality | Jonathon | 8 | 2017-03-22: 5; 2017-03-24: 5
| Xiaoyu | 8 | 2017-03-22: 5
| Andrew | 5 | 2017-03-22: 4
| Total | 21 | 2017-03-22: 14