## Backlog
ID | Product Backlog Item | Assignee | Priority | Difficulty | EST(Hrs) | Status
15 | Iterative deepening implemented | Jonathon | MID | HIGH | 10 | open
16 | Alpha-beta pruning implemented across one level | Andrew | MID | HIGH | 5 | open
17 | Alpha-beta pruning implemented across all levels | Andrew | MID | HIGH | 3 | open
18 | Minimax tree used for AI | Xiaoyu,Jonathon,Andrew | MID | HIGH | 5 | closed
19 | Computer looks ahead one move in tree | Xiaoyu | MID | HIGH | 3 | closed
20 | Animate Seeds | Jonathon | MID | MID | 5 | open
21 | Have AI make moves remotely | Xiaoyu | MID | MID | 5 | closed

## Sprint3
Sprint Goal | Volunteer | Original Estimate | 2017-04-02 | 2017-04-03 | 2017-04-04 | 2017-04-05 | 2017-04-07 | 2017-04-09 | Sprint Review
Allow an AI to play random moves against a player, add client/server functionality | Jonathon | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Xiaoyu | 3 | 3 | 2 | 2 | 1 | 0
| Andrew | 2 | 2 | 2 | 2 | 1 | 1 | 1
| Total | 7 | 7 | 6 | 6 | 4 | 3 | 3