## Backlog
ID | Product Backlog Item | Assignee | Priority | Difficulty | EST(Hrs) | Sprint
1 | Determine game states | Jonathon | HIGH | LOW | 1 | 1
2 | Text buttons as placeholders for seeds across the board | Xiaoyu | HIGH | MID | 3 | 1
3 | User sees a display of current board state | Xiaoyu | HIGH | MID | 2 | 1
4 | User gets response (invalid) if proposing an invalid move | Andrew | HIGH | LOW | 1 | 1
5 | User enters a move by typing position | Andrew | HIGH | LOW | 2 | 1
6 | User launches program and sees a title/introduction screen | Xiaoyu | HIGH | MID | 2 | 1
7 | Turn clock ticks by seconds | Jonathon | HIGH | MID | 2 | 1
8 | Round count | Xiaoyu | HIGH | MID | 2 | 1
9 | Ability to declare a player the game winner | Xiaoyu | HIGH | MID | 2 | 1
10 | Display current player turn | Xiaoyu | HIGH | MID | 2 | 1
11 | Simulate a "normal" match | Xiaoyu | HIGH | MID | 2 | 1
12 | Game checked to determine if max moves exceeded | Jonathon | HIGH | MID | 2 | 1
13 | User can click to indicate a move | Xiaoyu | HIGH | MID | 2 | 1
14 | Implement a seed class | Jonathon | MID | HIGH | 3 | 2
15 | Iterative deepening implemented | Jonathon | MID | HIGH | 10 | 4
16 | Alpha-beta pruning implemented across one level | Andrew | MID | HIGH | 5 | 3
17 | Alpha-beta pruning implemented across all levels | Andrew | MID | HIGH | 3 | 3
18 | Minimax tree used for AI | Xiaoyu | MID | HIGH | 5 | 2
19 | Computer looks ahead one move in tree | Xiaoyu | MID | HIGH | 3 | 2
20 | Computer can randomly select a valid move | Jonathon | MID | HIGH | 4 | 2
21 | Computer identifies all valid moves | Jonathon | MID | HIGH | 3 | 2

## Burndown
Sprint Goal |  | Original Estimate | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint Review
Create a game that would fool a 4 year old, display a game board |  | 21 | 14
| Total | 21 | 14