## Backlog
ID | Product Backlog Item | Assignee | Priority | Difficulty | EST(Hrs) | Sprint | Sprint Added | Status
1 | Determine game states | Jonathon | HIGH | LOW | 1 | 1 | 0 | closed
2 | Text buttons as placeholders for seeds across the board | Xiaoyu | HIGH | MID | 3 | 1 | 0 | closed
3 | User sees a display of current board state | Xiaoyu | HIGH | MID | 2 | 1 | 0 | closed
4 | User gets response (invalid) if proposing an invalid move | Andrew | HIGH | LOW | 1 | 1 | 0 | closed
5 | User enters a move by typing position | Andrew | HIGH | LOW | 2 | 1 | 0 | closed
6 | User launches program and sees a title/introduction screen | Xiaoyu | HIGH | MID | 2 | 1 | 0 | closed
7 | Turn clock ticks by seconds | Jonathon | HIGH | MID | 2 | 1 | 0 | closed
8 | Round count | Xiaoyu | HIGH | MID | 2 | 1 | 0 | closed
9 | Ability to declare a player the game winner | Xiaoyu | HIGH | MID | 2 | 1 | 0 | closed
10 | Display current player turn | Xiaoyu | HIGH | MID | 2 | 1 | 0 | closed
11 | Simulate a "normal" match | Xiaoyu | HIGH | MID | 2 | 1 | 0 | closed
12 | Game checked to determine if max moves exceeded | Jonathon | HIGH | MID | 2 | 1 | 0 | closed
13 | User can click to indicate a move | Xiaoyu | HIGH | MID | 2 | 1 | 0 | closed
14 | Implement a seed class | Jonathon | MID | HIGH | 3 | 2 | 0 | open
15 | Iterative deepening implemented | Jonathon | MID | HIGH | 10 | 3 | 0 | open
16 | Alpha-beta pruning implemented across one level | Andrew | MID | HIGH | 5 | 3 | 0 | open
17 | Alpha-beta pruning implemented across all levels | Andrew | MID | HIGH | 3 | 3 | 0 | open
18 | Minimax tree used for AI | Xiaoyu | MID | HIGH | 5 | 2 | 0 | open
19 | Computer looks ahead one move in tree | Xiaoyu | MID | HIGH | 3 | 2 | 0 | open
20 | Computer can randomly select a valid move | Jonathon | MID | HIGH | 4 | 2 | 0 | open
21 | Computer identifies all valid moves | Jonathon | MID | HIGH | 3 | 2 | 0 | open
22 | allow user to select 1 human v AI, 2 human or 2 AI players | Xiaoyu | MID | LOW | 1 | 1 | 1 | closed
23 | separate GUI into screens | Xiaoyu | HIGH | HIGH | 3 | 2 | 1 | open
24 | merge project into MVC framework | Jonathon | HIGH | MID | 2 | 2 | 1 | open
25 | turn clock ends turn if expired | Jonathon | MID | MID | 2 | 2 | 1 | open

## Burndown
Sprint # | Goal | Original Estimate | Sprint 1 | Sprint 2 | Sprint 3 | Sprint Review
1 | Create a game that would fool a 4 year old, display a game board | 21 | 11
2 | Allow an AI to play random moves against a player, add client/server functionality
|  | 21 | 11