## Backlog
ID | Product Backlog Item | Assignee | Priority | Difficulty | EST(Hrs)
1 | Determine game states | Jonathon | HIGH | LOW | 1
2 | Text buttons as placeholders for seeds across the board | Xiaoyu | HIGH | MID | 3
3 | User sees a display of current board state | Xiaoyu | HIGH | MID | 2
4 | User gets response (invalid) if proposing an invalid move | Andrew | HIGH | LOW | 1
5 | User enters a move by typing position | Andrew | HIGH | LOW | 2
6 | User launches program and sees a title/introduction screen | Xiaoyu | HIGH | MID | 2
7 | Turn clock ticks by seconds | Jonathon | HIGH | MID | 2
8 | Round count | Xiaoyu | HIGH | MID | 2
9 | Ability to declare a player the game winner | Xiaoyu | HIGH | MID | 2
10 | Display current player turn | Xiaoyu | HIGH | MID | 2
11 | Simulate a "normal" match | Xiaoyu | HIGH | MID | 2
12 | Game checked to determine if max moves exceeded | Jonathon | HIGH | MID | 2
13 | User can click to indicate a move | Xiaoyu | HIGH | MID | 2
14 | Allow user to select between 2 humans, 1 human v AI, or 2 Ais | Xiaoyu | MID | LOW | 1

## Sprint1
Sprint Goal | Volunteer | Original Estimate | 2017-03-06 | 2017-03-08 | 2017-03-10 | 2017-03-12 | 2017-03-14 | 2017-03-16 | 2017-03-18 | 2017-03-20 | 2017-03-21 | Sprint Review
Create a game that would fool a 4 year old, display a game board | Jonathon | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Xiaoyu | 11 | 9 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Andrew | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 16 | 14 | 8 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0